## TF
TRUST FUND UTILIZATION
Consolidated Quarterly Report on Government Funded Project/Programs/Activities
For the period ended March 31, 2018
Municipality of Bayog, Zamboanga del Sur
Name of Program/Project/Activity | Location | Total Cost | Date Started | Target date of Completion | Project Status |  | No. of Extension | Remarks
[5 empty] | % of Completion | Total cost to date
DILG BUB of 2014 - Salintubig Project | Brgy. Liba, Bubuan, Canoayan & Deporehan | 7500000 | Feb. 2015 | Jun. 2015 | 100% | 7500000 |  | completed
DILG BUB of 2014 - Rehab of River Control | Poblacion Bayog, ZDS | 3600000 | Mar. 2015 | Jul. 2015 | 100% | 3600000 |  | completed
DILG BUB of 2015 - Rehab of River Control | Poblacion Bayog, ZDS | 13500000 | Mar. 2015 | Aug. 2015 | 100% | 13500000 |  | completed
DILG-LGSF - Salawagan Foot Bridge | Salawagan Bayog, ZDS | 8665000 | 2016-06-01 | 2017-12-01 | 83% | 7544050 |  | on going
DILG-LGSF - Rechanelling of Bayog Creek | Poblacion Bayog, ZDS | 8235000 | 2016-06-01 | 2017-12-01 | 84% | 6804168.76 |  | on going
DILG-LGSF/ADM - Improvement of Water System | Poblacion Bayog, ZDS | 5000000 | 2017-10-01 | 2017-12-01 |  |  |  | on going
DILG-LGSF /ADM- Improvement of Municipal Streets | Poblacion Bayog, ZDS | 10000000 | 2017-10-01 | 2017-12-01 | 77.89% | 7789413 |  | on going
DAR BUB of 2014 - Concreting of Line Canal | Poblacion Bayog, ZDS | 2300000 | Sept. 2015 | Jan. 2016 | 100% | 2300000 |  | completed
DPWH- Concreting of Farm to Market Road | P4 Brgy. Damit, Bayog, ZDS | 7800942 | Jan. 15, 2015 | Apr. 2015 | 100% | 7800942 |  | completed
Construction of Early Childhood Dev't Center | Poblacion Bayog, ZDS | 2500000 | 2016-06-01 |  | 100% | 2500000 |  | completed
DA BUB of 2014 - Concreting of Line Canal | Poblacion Bayog, ZDS | 1865000 | Nov. 25, 2015 | Feb. 2016 | 100% | 1865000 |  | completed
DA BUB - Const/rehab of Balumbonan FMR | Balumbonan, Bayog, ZDS | 2400000 | 2016-06-01 |  | 100% | 2084350 |  | completed
DA - Village Type Corn Processing Plant | Dipili, Bayog ZDS | 4500000 |  |  | 0% | 0 |  | not yet started
DA - Palayshed at Brgy. Pulangbato | Brgy. Pulangbato, Bayog, ZDS | 150000 | Dec. 2015 |  | 100% | 150000 |  | completed
DA - Muti-purpose Drying Pavement | Brgy. San Isidro, Bayog, ZDS | 190000 | Nov. 2015 |  | 100% | 190000 |  | completed
DA - Palayshed at Brgy. Damit | Brgy. Damit, Bayog, ZDS | 150000 | Mar. 2014 | Nov. 2015 | 100% | 150000 |  | completed
DA - Farmers Training Center P1 | Brgy. Kahayagan, Bayog, ZDS | 1000000 | Nov. 2013 | Mar. 2014 | 100% | 1000000 |  | completed
DA - Muti-purpose Drying Pavement | Brgy. Depase & Salawagan, Bayog, ZDS | 380000 | Dec. 2014 | Nov. 2015 | 100% | 380000 |  | completed
DA - Village Type Rubber Processing Plant | Brgy. Depase, Bayog, ZDS | 1750000 | Sept. 2013 | Nov. 2015 | 100% | 1750000 |  | completed
DA - Contruction of Small Farm Reservoir | Brgy. Depase, Bayog, ZDS | 250000 | CY 2017 | CY 2017 | 100% | 248000 |  | completed
DA-Contruction of Farmers Training Center - Phase II | Brgy. Kahayagan, Bayog, ZDS | 1000000 |  |  | 65.74% | 657363.41 |  | on going
DOH - Repair/Renovation of RHU - TB DOTS | Poblacion Bayog, ZDS | 200000 |  | 2017-12-01 | 90% | 180000 |  | on going
DENR-Construction of MRF at Eco Park | Brgy. Kahayagan, Bayog, ZDS | 300000 |  |  | 100% | 299939 |  | completed
We hereby certify that we have reviewed the contents and hereby attest the veracity and correctness of the data or information contained in this document.
SGD. DIOSALDE M. LUMASAG. C.E. | SGD. JOEMAR L. ARANETA, CPA | SGD. MIGUELA B. ARNOCO |  | SGD. NORA M. PAREDES |  | SGD. LEONARDO L. BABASA JR., MBA, CPA
Municipal Engineer | Municipal Accountant | Municipal Treasurer |  | Municipal Agriculturist |  | Municipal Mayor